## Form_Extracted_Records
Source_Form | ID | InitiativeID | InitiativeName | DivisionCode | FiscalYear | FiscalMonth | FiscalQuarter | VZZ_CostClass | VZZ_WorkType | LaborSurvey_Category | Activity_Type | Source_System | CapEx_Eligible_Pct | Hours_Logged | ActualSpend_USD | BudgetAmount_USD | ForecastSpend_USD | CumulativeSpend_USD | PassingUnits | Asset_Life_Years | Depreciation_Annual_USD | SiteCity | SiteState | SiteZipCode | SiteSwitchCode | RegionalSwitchCode | RegionalMarket | RegionalState | OperationsCluster | Engineer_ID | Team | Miles_Driven | DriveTests_Completed | Pre_Post_Flag | Milestones_Completed | ProjectStartDate | ProjectEndDate | Project_Status | TechnologyGeneration
Form_01_Redstone_Bluffs_Jan2022.docx | FORM-001 | 6770487 | RDST-BLUFFS RDSTXTAA H2104 D11 W3 FIBER LINK | 871 | 2022 | 1 | Q1 | Expansion | Copper — Legacy Upgrade | New Construction | Build Milestone | Build Milestone Tracker | 85 | 32 | 2256.94 | 52000 | 55000 | 2256.94 | 412 | 15 | 3467 | REDSTONE BLUFFS | TX | 79701 | RDSTXTXA | RDSTXTAA | Redstone Bluffs | TX | TX Gulf | ENG-0071 | Network Engineering | 124.5 | 2 | Pre | 3 | 2022-01-10 | Ongoing | In Progress | Fiber
Form_02_Redstone_Bluffs_Nov2023.docx | FORM-002 | 6770487 | RDST-BLUFFS RDSTXTAA H2104 D11 W3 FIBER LINK | 871 | 2023 | 11 | Q4 | Expansion | Copper — Legacy Upgrade | Engineering & Design | Build Milestone | Build Milestone Tracker | 90 | 68 | 163000.28 | 150000 | 160000 | 286122.69 | 412 | 15 | 10000 | REDSTONE BLUFFS | TX | 75201 | RDSTXTXA | RDSTXTAA | Redstone Bluffs | TX | TX Gulf | ENG-0071 | Network Engineering | 210 | 5 | Post | 8 | 2022-01-10 | Ongoing | In Progress | Fiber
Form_03_Lakeview_Crossing_Jan2022.docx | FORM-003 | 6214853 | LKVIEW-XING LKVWOHBB H3002 D18 N15 FIBER EXPN | 872 | 2022 | 1 | Q1 | Expansion | Copper — Legacy Upgrade | New Construction | Build Milestone | Build Milestone Tracker | 80 | 40 | 24548.5 | 30000 | 28000 | 24548.5 | 178 | 10 | 2455 | LAKEVIEW CROSSING | OH | 44101 | LKVWOHXB | LKVWOHBB | Lakeview Crossing | OH | Great Lakes | ENG-0034 | System Performance | 88 | 3 | Pre | 4 | 2022-01-15 | 2023-12-31 | In Progress | FTTP
Form_04_Lakeview_Crossing_Apr2023.docx | FORM-004 | 6214853 | LKVIEW-XING LKVWOHBB H3002 D18 N15 FIBER EXPN | 872 | 2023 | 4 | Q2 | Expansion | Copper — Legacy Upgrade | Replacement | Analysis Report | xLPT | 75 | 52 | 43550.46 | 40000 | 42000 | 173747.34 | 178 | 10 | 4355 | LAKEVIEW CROSSING | OH | 44101 | LKVWOHXB | LKVWOHBB | Lakeview Crossing | OH | Great Lakes | ENG-0034 | System Performance | 145 | 4 | Post | 6 | 2022-01-15 | 2023-12-31 | Completed | FTTP
Form_05_Pineridge_Flats_Jan2022.docx | FORM-005 | 6583941 | PNRDGE-MDU 340 UNIT 1802 VALLEY DR, PINERIDGE | 873 | 2022 | 1 | Q1 | Expansion | MDU Fiber Drop | New Construction | Store Visit | Xcelerate | 95 | 28 | -42984.96 | 50000 | 45000 | -42984.96 | 52 | 10 | 5000 | PINERIDGE FLATS | GA | 30301 | PNRDGAXA | PNRDGACC | Pineridge Flats | GA | Southeast | ENG-0112 | Network Assurance | 62 | 1 | Pre | 2 | 2022-01-05 | 2023-11-30 | On Hold | FTTP
Form_06_Pineridge_Flats_Feb2022.docx | FORM-006 | 6583941 | PNRDGE-MDU 340 UNIT 1802 VALLEY DR, PINERIDGE | 873 | 2022 | 2 | Q1 | Expansion | MDU Fiber Drop | New Construction | Build Milestone | Build Milestone Tracker | 95 | 16 | 2651.14 | 5000 | 4500 | -40333.82 | 52 | 10 | 265 | PINERIDGE FLATS | GA | 30301 | PNRDGAXA | PNRDGACC | Pineridge Flats | GA | Southeast | ENG-0112 | Network Assurance | 35 | 1 | Pre | 1 | 2022-01-05 | 2023-11-30 | In Progress | FTTP
Form_07_Hollow_Creek_Jan2022.docx | FORM-007 | 6421076 | HLWCRK HLWCCODD H5107 DAM_4 GF PASSINGS | 874 | 2022 | 1 | Q1 | Expansion | Greenfield Fiber Build | New Construction | Build Milestone | Build Milestone Tracker | 100 | 44 | 18637.75 | 25000 | 22000 | 18637.75 | 247 | 20 | 932 | HOLLOW CREEK | CO | 80203 | HLWCCOXA | HLWCCODD | Hollow Creek | CO | Rocky Mountain | ENG-0058 | Network Engineering | 178 | 2 | Pre | 5 | 2022-01-20 | 2023-12-15 | In Progress | Fiber
Form_08_Hollow_Creek_Feb2022.docx | FORM-008 | 6421076 | HLWCRK HLWCCODD H5107 DAM_4 GF PASSINGS | 874 | 2022 | 2 | Q1 | Expansion | Greenfield Fiber Build | Engineering & Design | Site Survey | Xcelerate | 100 | 12 | 1362.08 | 2000 | 1800 | 19999.83 | 247 | 20 | 68 | HOLLOW CREEK | CO | 80203 | HLWCCOXA | HLWCCODD | Hollow Creek | CO | Rocky Mountain | ENG-0058 | Network Engineering | 95 | 1 | Pre | 1 | 2022-01-20 | 2023-12-15 | In Progress | Fiber
Form_09_Silvergate_Jan2022.docx | FORM-009 | 6809570 | SLVGT CABLE EXTENSION 8814-7TH ST NW | 875 | 2022 | 1 | Q1 | Expansion | MDU Fiber Drop | New Construction | Build Milestone | Build Milestone Tracker | 95 | 76 | 217266.58 | 200000 | 215000 | 217266.58 | 6 | 10 | 21727 | SILVERGATE | AZ | 85001 | SLVGAZXA | SLVGAZEE | Silvergate | AZ | Desert SW | ENG-0099 | Network Assurance | 310 | 4 | Pre | 7 | 2022-01-08 | 2023-06-30 | Completed | FTTP
Form_10_Silvergate_Aug2022.docx | FORM-010 | 6809570 | SLVGT CABLE EXTENSION 8814-7TH ST NW | 875 | 2022 | 8 | Q3 | Expansion | MDU Fiber Drop | Replacement | Drive Test | DMAT | 88 | 58 | 41672.94 | 38000 | 40000 | 263737.83 | 6 | 10 | 4167 | SILVERGATE | AZ | 85001 | SLVGAZXA | SLVGAZEE | Silvergate | AZ | Desert SW | ENG-0099 | Network Assurance | 220 | 6 | Post | 4 | 2022-01-08 | 2023-06-30 | Completed | FTTP

## Classification_Results
Record_ID | Engineer_ID | Initiative_Name | Classification | Confidence_Score | CapEx_Pct | OpEx_Pct | Labor_Category | Evidence_Note | Rule_Version | Overridden | Override_Value | Timestamp
FORM-001 | ENG-0071 | RDST-BLUFFS FIBER LINK | CapEx | 91 | 85 | 15 | New Construction | High CapEx eligibility (85%). Expansion cost class. Build Milestone activity. 3 milestones completed. | v2.1.0 | FALSE |  | 2026-05-21
FORM-002 | ENG-0071 | RDST-BLUFFS FIBER LINK | CapEx | 93 | 90 | 10 | Engineering & Design | High CapEx eligibility (90%). Expansion cost class. Build Milestone activity. 8 milestones completed. | v2.1.0 | FALSE |  | 2026-05-21
FORM-003 | ENG-0034 | LKVIEW-XING FIBER EXPN | CapEx | 87 | 80 | 20 | New Construction | High CapEx eligibility (80%). Expansion cost class. Build Milestone activity. 4 milestones completed. | v2.1.0 | FALSE |  | 2026-05-21
FORM-004 | ENG-0034 | LKVIEW-XING FIBER EXPN | CapEx | 82 | 75 | 25 | Replacement | High CapEx eligibility (75%). Expansion cost class. Analysis Report activity. | v2.1.0 | FALSE |  | 2026-05-21
FORM-005 | ENG-0112 | PNRDGE-MDU PINERIDGE | CapEx | 92 | 95 | 5 | New Construction | Very high CapEx eligibility (95%). MDU Fiber Drop cost class. 2 milestones completed. | v2.1.0 | FALSE |  | 2026-05-21
FORM-006 | ENG-0112 | PNRDGE-MDU PINERIDGE | CapEx | 93 | 95 | 5 | New Construction | Very high CapEx eligibility (95%). MDU Fiber Drop. Build Milestone. 1 milestone completed. | v2.1.0 | FALSE |  | 2026-05-21
FORM-007 | ENG-0058 | HLWCRK GREENFIELD FIBER | CapEx | 97 | 100 | 0 | New Construction | 100% CapEx eligibility. Greenfield Fiber Build. Build Milestone. 5 milestones completed. | v2.1.0 | FALSE |  | 2026-05-21
FORM-008 | ENG-0058 | HLWCRK GREENFIELD FIBER | CapEx | 95 | 100 | 0 | Engineering & Design | 100% CapEx eligibility. Greenfield Fiber Build. Site Survey activity. | v2.1.0 | FALSE |  | 2026-05-21
FORM-009 | ENG-0099 | SLVGT CABLE EXTENSION | CapEx | 92 | 95 | 5 | New Construction | Very high CapEx eligibility (95%). MDU Fiber Drop. Build Milestone. 7 milestones completed. | v2.1.0 | FALSE |  | 2026-05-21
FORM-010 | ENG-0099 | SLVGT CABLE EXTENSION | CapEx | 86 | 88 | 12 | Replacement | High CapEx eligibility (88%). MDU Fiber Drop. Drive Test activity. 4 milestones completed. | v2.1.0 | FALSE |  | 2026-05-21